## Master Onepager
Theory of change - River Guardians(Straznicy Rzek) (07.2019 - 06.2020)
Szef: XXX
Zespół celowy: Osoba 1, Osoba 2, Osoba 3
Goal:
Long term goal: Rivers, are cherished and protected in harmony with humans.
Problems:
Low social pressure on the management of waters and low people in the use of rivers. Water management authorities don't implement best practices"?
Low social involvement in the protection of rivers
Low awareness of offices and society regarding naturalness of rivers, ecosystem services, causes of drought, ways of retention, environmental costs of river regulation.

## Q1
Monitoring of implementation | 13.57%
% of Budget Involvment | 28%
Highlights/threats | Two very important interventions: Żylica River - suspending the river degradating actions in EU finaced project; Bug river - active participation to halt plans of building river embankment on Bug river. Detailed report with mapping all maintenance is not cost efficient, thus, we should finalize the report in ohter way
Comments / ad-hoc actions | x
Outcome | Output | Actions/ sub-actions | Monitoring % of implementation | Highlights/threats | Comments
1. Ecological condition of the Polish rivers is constantly monitored thanks to the network of “River Guardians” active in all relevant voivodeships for HCV small rivers. | Report on scale and environmental consequences of river maintenance conducted in 2019 y. prepared and disseminated | Tenders concerning riverregulations and river maintenance constantly monitored. | 25% | Detailed report with mapping all maintenance is not cost efficency (external assistance) and though we should decide how to finalize that action | To be decided if and how to implement that action
Tenders concerning river restoration constantly monitored.
2.Polish Rivers are protected due to interventions based on an Early Warning System | 10 interventions to halt or to green harmful regulation or maintenance works or other problems on rivers (eg. water pollution, waste in rivers) by WWF | Upgrading and sustaining GIS System on web site | 20% | Interventions on: Bug river, Żylica
| 3 expertises | Water management and nature conservation authorities andenvironmental NGOs in 16voivodeships informed about plans of harmfuldevelopments threatening SR-HNCV. | 0%
3. Increasing social pressure on the government and local government offices leads to decrease in river damage |  | Cooperation with RZGW Wrocław
Maintaining and improving an Early warning system that informs about plans of harmfuldevelopments (civil engineering investments, maintenance works) in 16 voivodeships, in areas that are relevant for the conservation for the Polish HCV small rivers.
Collecting data ef tenders on rivers in 2018 and 2019
| River Guardians network created and developed | Creating and developing the network of River Guardians | 25% | still developing
| 100 sections of rivers inspected in the field for the state of preservation Status of minimum 100 sections (of rivers documented by River Guardians.) | Collecting good examples of proceeding maintenance work | 20%
Identifying and recruiting NGOsand individuals - the RiverGuardians - in 16 voivodeships.
| 100 sections of rivers are adopted by River Guardians | Developing and implementingplan of activities for the RiverGuardians (communication andeducation activities, raising public awareness). | 10%
| 50 contracts for volunteering signed. | Coordination of River adoption program, including: Collection of applications, Production of gifts for RG, Signing contracts, Communication with the RG | 10%
| 50 NEW River Guardians recruited and operating in at least 16 voivodeships in FY20.(about 300-350 RG) | Collection of applications, Production of gifts for RG, Signing contracts, | 15%
Identifying leaders of volunteers
| Plan of activities for the River | Communication with the Guardians | 25%
| Guardians developed and implemented (documenting river status, interventions related to the protection of river, species and their habitats, communication and education activities, rising public awareness) | Improving communication with RG using new technologies | 10%
Upgrading website
| 10 interventions to halt or to green harmful regulation or maintenance works or other problems on rivers (eg. water pollution, waste in rivers) by River Guardians | Starting cooperation with organized groups, eg. schools, scouts, anglers, kayaking groups etc. | 30%
| 4 training workshop fort he River Guardians held | UPM Raflatac, GEBERIT - Guards of Rivers: meetings with Partners as needed (4*7=28), reports (2*7=14), calls (2*3,5=7), communication materials accepting (20*2=40), workshops conducting (8*7=56) | 0%
Other ad hoc interesting possibilities: consultations on projects development, meetings as needed, materials accepting=7
| 2 Workshops and trainings for regional River Guardians coordinators or RG Volunteers held | Other ad hoc interesting possibilities=7 | 0%
Communication:
Communication 1
Communication 2
| Experience from the third year of River Guardians operation summarized in form of a report | Communication 3 | 0%

## Q2
Monitoring of implementation | 29.17%
% of Budget Involvment | 47%
Highlights/threats | Two very important interventions: Żylica River - suspending the river degradating actions in EU finaced project; Bug river - active participation to halt plans of building river embankment on Bug river. We decided to continue reporting of maintenance works using xls tabels, without mapping it on GIS system
Outcome | Output | Actions/ sub-actions | Monitoring % of implementation | Highlights/threats | % of Budget Involvment
1. Ecological condition of the Polish rivers is constantly monitored thanks to the network of “River Guardians” active in all relevant voivodeships for HCV small rivers. | Report on scale and environmental consequences of river maintenance conducted in 2019 y. prepared and disseminated | Tenders concerning riverregulations and river maintenance constantly monitored. | 25% | We decided to report maintenance works in 2019 using ionly data collected in excell tabels (without mapping) Work will be commisioned in february | To be decided if and how to implement that action
|  | Tenders concerning river restoration constantly monitored. | 50%
2.Polish Rivers are protected due to interventions based on an Early Warning System | 10 interventions to halt or to green harmful regulation or maintenance works or other problems on rivers (eg. water pollution, waste in rivers) by WWF | Upgrading and sustaining GIS System on web site | 40% | Bug, Żylica, Srebrny Potok, Rogoźnik,
| 3 expertises | Water management and nature conservation authorities andenvironmental NGOs in 16voivodeships informed about plans of harmfuldevelopments threatening SR-HNCV. | 0%
3. Increasing social pressure on the government and local government offices leads to decrease in river damage |  | Cooperation with RZGW Wrocław | 10% | Due to intervention on Żylica we condyucted workshop for RZGW Kraków
|  | Maintaining and improving an Early warning system that informs about plans of harmfuldevelopments (civil engineering investments, maintenance works) in 16 voivodeships, in areas that are relevant for the conservation for the Polish HCV small rivers. | 40%
|  | Collecting data ef tenders on rivers in 2018 and 2019 | 45%
| River Guardians network created and developed | Creating and developing the network of River Guardians | 50%
| 100 sections of rivers inspected in the field for the state of preservation Status of minimum 100 sections (of rivers documented by River Guardians.) | Collecting good examples of proceeding maintenance work | 25%
|  | Identifying and recruiting NGOsand individuals - the RiverGuardians - in 16 voivodeships. | 50%
| 100 sections of rivers are adopted by River Guardians | Developing and implementingplan of activities for the RiverGuardians (communication andeducation activities, raising public awareness). | 50%
| 50 contracts for volunteering signed. | Coordination of River adoption program, including: Collection of applications, Production of gifts for RG, Signing contracts, Communication with the RG | 15%
| 50 NEW River Guardians recruited and operating in at least 16 voivodeships in FY20.(about 300-350 RG) | Collection of applications, Production of gifts for RG, Signing contracts, | 30%
Identifying leaders of volunteers
| Plan of activities for the River | Communication with the Guardians | 40%
| Guardians developed and implemented (documenting river status, interventions related to the protection of river, species and their habitats, communication and education activities, rising public awareness) | Improving communication with RG using new technologies | 25%
Upgrading website
| 10 interventions to halt or to green harmful regulation or maintenance works or other problems on rivers (eg. water pollution, waste in rivers) by River Guardians | Starting cooperation with organized groups, eg. schools, scouts, anglers, kayaking groups etc. | 30%
| 4 training workshop fort he River Guardians held | UPM Raflatac, GEBERIT - Guards of Rivers: meetings with Partners as needed (4*7=28), reports (2*7=14), calls (2*3,5=7), communication materials accepting (20*2=40), workshops conducting (8*7=56) | 25%
Other ad hoc interesting possibilities: consultations on projects development, meetings as needed, materials accepting=7
| 2 Workshops and trainings for regional River Guardians coordinators or RG Volunteers held | Other ad hoc interesting possibilities=7 | 0%
Communication:
Communication 1
Communication 2
| Experience from the third year of River Guardians operation summarized in form of a report | Communication 3 | 0%

## Q3
Monitoring of implementation | #DIV/0!
% of Budget Involvment | 28%
Highlights/threats | x
Outcome | Output | Actions/ sub-actions | Monitoring % of implementation | Highlights/threats | % of Budget Involvment
1. Ecological condition of the Polish rivers is constantly monitored thanks to the network of “River Guardians” active in all relevant voivodeships for HCV small rivers. | Report on scale and environmental consequences of river maintenance conducted in 2019 y. prepared and disseminated | Tenders concerning riverregulations and river maintenance constantly monitored.
Tenders concerning river restoration constantly monitored.
2.Polish Rivers are protected due to interventions based on an Early Warning System | 10 interventions to halt or to green harmful regulation or maintenance works or other problems on rivers (eg. water pollution, waste in rivers) by WWF | Upgrading and sustaining GIS System on web site
| 3 expertises | Water management and nature conservation authorities andenvironmental NGOs in 16voivodeships informed about plans of harmfuldevelopments threatening SR-HNCV.
3. Increasing social pressure on the government and local government offices leads to decrease in river damage |  | Cooperation with RZGW Wrocław
Maintaining and improving an Early warning system that informs about plans of harmfuldevelopments (civil engineering investments, maintenance works) in 16 voivodeships, in areas that are relevant for the conservation for the Polish HCV small rivers.
Collecting data ef tenders on rivers in 2018 and 2019
| River Guardians network created and developed | Creating and developing the network of River Guardians
| 100 sections of rivers inspected in the field for the state of preservation Status of minimum 100 sections (of rivers documented by River Guardians.) | Collecting good examples of proceeding maintenance work
Identifying and recruiting NGOsand individuals - the RiverGuardians - in 16 voivodeships.
| 100 sections of rivers are adopted by River Guardians | Developing and implementingplan of activities for the RiverGuardians (communication andeducation activities, raising public awareness).
| 50 contracts for volunteering signed. | Coordination of River adoption program, including: Collection of applications, Production of gifts for RG, Signing contracts, Communication with the RG
| 50 NEW River Guardians recruited and operating in at least 16 voivodeships in FY20.(about 300-350 RG) | Collection of applications, Production of gifts for RG, Signing contracts,
Identifying leaders of volunteers
| Plan of activities for the River | Communication with the Guardians
| Guardians developed and implemented (documenting river status, interventions related to the protection of river, species and their habitats, communication and education activities, rising public awareness) | Improving communication with RG using new technologies
Upgrading website
| 10 interventions to halt or to green harmful regulation or maintenance works or other problems on rivers (eg. water pollution, waste in rivers) by River Guardians | Starting cooperation with organized groups, eg. schools, scouts, anglers, kayaking groups etc.
| 4 training workshop fort he River Guardians held | UPM Raflatac, GEBERIT - Guards of Rivers: meetings with Partners as needed (4*7=28), reports (2*7=14), calls (2*3,5=7), communication materials accepting (20*2=40), workshops conducting (8*7=56)
Other ad hoc interesting possibilities: consultations on projects development, meetings as needed, materials accepting=7
| 2 Workshops and trainings for regional River Guardians coordinators or RG Volunteers held | Other ad hoc interesting possibilities=7
Communication:
Communication 1
Communication 2
| Experience from the third year of River Guardians operation summarized in form of a report | Communication 3

## Q4
Monitoring of implementation | #DIV/0!
% of Budget Involvment | 28%
Highlights/threats | x
Outcome | Output | Actions/ sub-actions | Monitoring % of implementation | Highlights/threats | % of Budget Involvment
1. Ecological condition of the Polish rivers is constantly monitored thanks to the network of “River Guardians” active in all relevant voivodeships for HCV small rivers. | Report on scale and environmental consequences of river maintenance conducted in 2019 y. prepared and disseminated | Tenders concerning riverregulations and river maintenance constantly monitored.
Tenders concerning river restoration constantly monitored.
2.Polish Rivers are protected due to interventions based on an Early Warning System | 10 interventions to halt or to green harmful regulation or maintenance works or other problems on rivers (eg. water pollution, waste in rivers) by WWF | Upgrading and sustaining GIS System on web site
| 3 expertises | Water management and nature conservation authorities andenvironmental NGOs in 16voivodeships informed about plans of harmfuldevelopments threatening SR-HNCV.
3. Increasing social pressure on the government and local government offices leads to decrease in river damage |  | Cooperation with RZGW Wrocław
Maintaining and improving an Early warning system that informs about plans of harmfuldevelopments (civil engineering investments, maintenance works) in 16 voivodeships, in areas that are relevant for the conservation for the Polish HCV small rivers.
Collecting data ef tenders on rivers in 2018 and 2019
| River Guardians network created and developed | Creating and developing the network of River Guardians
| 100 sections of rivers inspected in the field for the state of preservation Status of minimum 100 sections (of rivers documented by River Guardians.) | Collecting good examples of proceeding maintenance work
Identifying and recruiting NGOsand individuals - the RiverGuardians - in 16 voivodeships.
| 100 sections of rivers are adopted by River Guardians | Developing and implementingplan of activities for the RiverGuardians (communication andeducation activities, raising public awareness).
| 50 contracts for volunteering signed. | Coordination of River adoption program, including: Collection of applications, Production of gifts for RG, Signing contracts, Communication with the RG
| 50 NEW River Guardians recruited and operating in at least 16 voivodeships in FY20.(about 300-350 RG) | Collection of applications, Production of gifts for RG, Signing contracts,
Identifying leaders of volunteers
| Plan of activities for the River | Communication with the Guardians
| Guardians developed and implemented (documenting river status, interventions related to the protection of river, species and their habitats, communication and education activities, rising public awareness) | Improving communication with RG using new technologies
Upgrading website
| 10 interventions to halt or to green harmful regulation or maintenance works or other problems on rivers (eg. water pollution, waste in rivers) by River Guardians | Starting cooperation with organized groups, eg. schools, scouts, anglers, kayaking groups etc.
| 4 training workshop fort he River Guardians held | UPM Raflatac, GEBERIT - Guards of Rivers: meetings with Partners as needed (4*7=28), reports (2*7=14), calls (2*3,5=7), communication materials accepting (20*2=40), workshops conducting (8*7=56)
Other ad hoc interesting possibilities: consultations on projects development, meetings as needed, materials accepting=7
| 2 Workshops and trainings for regional River Guardians coordinators or RG Volunteers held | Other ad hoc interesting possibilities=7
Communication:
Communication 1
Communication 2
| Experience from the third year of River Guardians operation summarized in form of a report | Communication 3

## Budget involvment
Budget involvment FY20
FY20 quarter | % of budget involvment
Q1
Q2
Q3
Q4